# 8-Bit Sheep AI Assistant — Project Plan v0.1

Mark

2026-05-28

## What We Are Building

An AI assistant platform that automates and assists with 8bs routine admin tasks — initially Sales (Severa) and Finance (Netvisor, Säästöpankki). The assistant is accessible via Discord, email, and a web UI. New use cases (skills) can be added without rebuilding the platform.

### What this is NOT

- A replacement for Severa or Netvisor — the assistant reads data from them and drafts actions for a human to confirm

- A full automation system on day one — v0.1 is read-only access with human-in-the-loop approval for any writes

- A long development project — the platform foundation already exists (open-source template), so we are deploying and configuring, not building from scratch

## Foundation: What Already Exists

The sunholo-data/ai-protocol-platform (MIT-licensed, public) is a production-ready platform template that provides:

- Google ADK agent framework (Google’s AI agent SDK)

- Cloud Run deployment (scale-to-zero, serverless)

- Terraform for dev/test/prod environments

- Skills system — add new AI capabilities as isolated modules

- MCP protocol — standard interface for connecting tools (Severa, Drive, etc.)

- Discord, email channel connectors (framework-level)

- Web UI for chat, debugging and analytics

- Firebase authentication

- CI/CD pipeline (GitHub Actions + Cloud Build)

This means Phase 0 and Phase 1 below are configuration and deployment work, not greenfield development.

## Phases

### Phase 0 — GCP Infrastructure Setup

Owner: Mark | Estimate: 8 hrs

| Task | Notes |
| --- | --- |
| Fork template to 8-bit-sheep GitHub org | Creates private internal repo |
| GCP projects: dev / test / prod | Parallel environments, same as template pattern |
| Terraform bootstrap | Service accounts, IAM, Cloud Run services |
| GitHub Actions CI/CD | Automated deploy on push to dev/test/prod branches |
| GitHub repo + Issues + Project board | Kanban board for task tracking (as requested) |
| Local dev environment docs | So others can run it locally without GCP credentials |

DoD: make dev starts the platform locally; push to dev branch auto-deploys to GCP dev environment.

### Phase 1 — Core Platform Deployment

Owner: Mark | Estimate: 8 hrs

| Task | Notes |
| --- | --- |
| Deploy backend + frontend to Cloud Run (dev) | Web UI accessible at 8bs dev URL |
| Firebase auth with 8bs Google Workspace | Sheep log in with their @8bitsh… Google accounts |
| Smoke tests + health checks | Automated verification that deploy succeeded |
| Basic “hello” skill end-to-end | Proves the chain works before adding real integrations |
| Analytics dashboard wired up | OpenTelemetry → Cloud Logging (GCP-internal, no 3rd-party) |

DoD: Any Sheep can open the web UI, log in with Google, and chat with the assistant. Usage visible in GCP console.

### Phase 2 — MCP Tool Connectors (Integrations)

Owner: Mark (lead) + delegatable | Estimate: 16 hrs total

Each connector is an isolated Python module exposing the external API as MCP tools. Read-only by default; write operations require explicit approval in Phase 3+.

#### 2a — Severa CRM/Hours (Mark, ~5 hrs)

- Authenticate with Severa REST API (OAuth token per-user)

- Tools: list_projects, get_hours, get_invoices, list_contacts

- Read-only. No write access in v0.1.

#### 2b — Netvisor Finance (Mark, ~5 hrs)

- Authenticate with Netvisor API

- Tools: get_invoices, get_salary_data, get_cost_entries

- Read-only. No write access in v0.1.

#### 2c — Säästöpankki Bank (Mark, ~4 hrs)

- Bank API authentication + account access

- Tools: get_transactions, get_balance

- Read-only. No write access in v0.1.

#### 2d — Google Drive (delegatable, ~2 hrs)

- Already partially supported by template

- Tools: list_files, read_doc, search_drive

DoD: Each connector has unit tests and can be called from the assistant CLI.

### Phase 3 — Initial Skills (Use Cases)

Owner: Mark (design) + delegatable (implementation) | Estimate: 12 hrs

Skills are the user-facing AI capabilities. Each skill combines the MCP connectors above with a focused prompt and workflow.

#### Skill 1 — Weekly Hours Summary (~3 hrs)

- “What hours have I logged this week in Severa?”

- Pushes summary to Discord DM or email on schedule

#### Skill 2 — Open Invoices & Cash Flow (~3 hrs)

- “Show me overdue invoices” / “What’s our current cash position?”

- Pulls from Severa (invoices) + Säästöpankki (balance)

#### Skill 3 — Monthly Finance Snapshot (~3 hrs)

- Combines Netvisor + Säästöpankki data

- Drafted summary for Finance review, not final output

#### Skill 4 — Project Status Briefing (~3 hrs)

- Pulls active projects + hours vs budget from Severa

- “Which projects are over/under budget?”

DoD: Each skill is accessible via the web UI, Discord, and email. Output is readable and correct based on real data from the APIs.

### Phase 4 — Channels

Owner: Mark (Discord) + delegatable (email) | Estimate: 6 hrs

| Channel | Estimate | Notes |
| --- | --- | --- |
| Discord bot | 3 hrs | Sheep can query the assistant in the 8bs Discord server |
| Email | 2 hrs | Send summary reports to a configured address on schedule |
| Web UI polish | 1 hr | Navigation, branding, basic analytics view |

DoD: Sheep can interact with the assistant via Discord @assistant what are my hours this week? and receive a reply.

### Stretch Goal — RAG Backend (Gemini Enterprise)

Owner: TBD | Estimate: 10 hrs

If Gemini Enterprise is available on the GCP projects: - Document ingestion from Google Drive (contracts, invoices, meeting notes) - “Find the clause about invoicing in the XYZ client contract” style queries - Builds the foundation for client-facing use cases later

This is explicitly out of scope for v0.1 unless Phase 0–4 finishes under budget.

## Task Allocation

| Phase | Hours | Mark | Delegatable |
| --- | --- | --- | --- |
| 0 — Infrastructure | 8 | 8 | 0 |
| 1 — Core Platform | 8 | 8 | 0 |
| 2 — Connectors | 19 | 17 | 2 (Drive) |
| 3 — Skills | 12 | 4 | 8 |
| 4 — Channels | 6 | 3 | 3 |
| PoC v0.1 total | 53 | 40 | 13 |
| RAG stretch | 10 | 2 | 8 |
| Project total (v0.1 + stretch) | 63 | 42 | 21 |

Remaining budget after v0.1: ~147 hrs for v0.2 enhancements, new skills, and client-facing work.

## What Can Be Delegated

The following tasks require no deep platform knowledge and are good learning tasks for contributors:

- Google Drive connector (Phase 2d) — well-documented API, clear interface

- Skills implementation (Phase 3) — each skill is a focused Python module with a clear spec; Mark provides the template

- Email channel (Phase 4) — template has the framework, configuration only

- GitHub issues / project board setup — kanban for the whole project

- Testing — writing test cases for connectors and skills, running them

- Documentation — README, user guide for each skill

Prerequisites for contributors: - Python basics - Google account with access to 8bs GCP dev project - make dev running locally (documented in repo)

## Out of Scope for v0.1

| Item | Reason |
| --- | --- |
| Severa write access (create hours, invoices) | Risk; requires separate approval decision |
| Netvisor write access | Same as above |
| Browser automation / Stagehand for Severa | Flaky and slow; Severa REST API now available |
| Client-facing deployment | After v0.1 is proven internally first |
| A2A marketplace (Gemini Enterprise) | Infrastructure for later — compatible by design, not deployed yet |
| Mobile app | Web UI covers this via browser |

## Estimate Basis

These estimates are calibrated against two prior deployments of the same platform template:

### Aitana Platform (internal, April–May 2026)

The Aitana v6 platform is the source of the public template. Its sprint history shows:

- Cloud infrastructure sprint: estimated 2.5 days, shipped on schedule

- Auth + permissions sprint: estimated 3.5 days, shipped on schedule

- No blown estimates across Phase 0–1 equivalent work

The post-May-2026 template (what 8bs will fork) has auth hardening, branding config, and fork ergonomics already built in — this removes most of the friction encountered in the early Aitana sprints.

### AIPLA — University of Copenhagen (May 2026)

A production fork of the same template for an AI-in-Physics learning project. Platform was deployed and operational within a comparable 40-hour window. The AIPLA fork is referenced at sunholo.com/aipla.

### What the estimates cover

| Phase | Risk | Notes |
| --- | --- | --- |
| 0–1 Infrastructure + deploy | Low | Mostly configuration; template does the heavy lifting |
| 2a Severa connector | Low–Medium | REST API now approved; auth pattern is standard OAuth |
| 2b Netvisor connector | Medium | Depends on API documentation quality |
| 2c Säästöpankki connector | Medium–High | Bank API auth complexity unknown until tested |
| 3–4 Skills + channels | Low | Template provides the framework; custom logic only |

The main estimate risk is API access complexity for Netvisor and Säästöpankki. If either requires per-user OAuth flows with poor documentation, add 2–4 hrs each. Severa is low-risk as the API is now confirmed and well-documented.

## Budget View

| Item | EUR |
| --- | --- |
| Mark — PoC v0.1 (40 hrs) | 4,000 |
| Contributor work (13 hrs) | 1,300 |
| Severa API upgrade (monthly) | 200/mth |
| GCP Cloud Run + Firebase (estimated) | ~50–100/mth |
| v0.1 one-off build cost | ~5,000 |
| Remaining budget for v0.2+ | ~15,000 |

## Definition of Done — v0.1 Pilot

v0.1 is complete when:

- Any Sheep can log in with their 8bs Google account

- Assistant can answer “what are my hours this week?” using live Severa data

- Assistant can answer “show me open invoices” using live Severa data

- Assistant can answer “what’s our bank balance?” using Säästöpankki data

- Discord bot responds to queries in the 8bs server

- Finance snapshot skill sends a weekly email summary

- All data access is read-only; no writes to any system

- Usage and errors are visible in the GCP console (no 3rd-party analytics)

- At least one Sheep other than Mark can add a new simple skill without Mark’s help

## Proposed Next Steps

- Mark: Fork template to 8bs GitHub org, create GitHub Project board with Issues mirroring this plan

- groner: Confirm GCP project names/IDs for 8bs (or confirm we create new ones)

- Leevi / designated Sheep: Set up Severa API token in Severa Settings → Integrations → REST API

- temeke (or anyone): Claim a delegatable task from Phase 3 or 4 once Phase 0–2 land

- Everyone: Agree on Discord server/channel for the bot to live in

## Questions Still Open

- GCP projects — do we create new 8bs-dev, 8bs-test, 8bs-prod projects, or use existing ones?

- GitHub org — 8-bit-sheep or different org name?

- Netvisor API — same approval as Severa, or still in discussion?

- Säästöpankki — what API access exists? (contact at bank, or existing Open Banking integration?)

- Discord — which server / which channel for the bot?

- Temeke’s start date — post-midsummer July slot works; align with Phase 3 start (after infra and connectors are done)